## Sheet1
Week # | Action | Comments
7 | Style theme & Wireframe finish Platform purchased
8 | Login page HTML/CSS done Database Tables with fake data created
9 | User/Admin directory HTML/CSS done Forgot password js/php done
10 | User Profile HTML/CSS done Login js/php done | 60%
11 | ACL HTML/CSS done User/Admin Directory js/php done | User/Admin functionality essential the same
12 | User Profile js/php done ACL js/php done | Linking to ACL from admin directory will be done this week
13 | Debug the crap out of it
14 | Import & Test | 90%
15 | Fix & Debug
16 | Prep for presentation | Presentation