## Reporting Period One
16
|  | Sue | Peres | Ingrid | Luis | PM | % complete | Planned Hours | hours spent
| Diagram user-system interaction |  |  |  |  | 2 |  | 2 | 0
| Planning and Meeting | 1.42 | 1.2 | 1.1 | 1.2 |  |  |  | 4.92
Week 1 | Define Use Cases |  |  | 0.33 | 0.25 |  |  | 10 | 0.58 |  | 11.7 | 6.87 | 7.17
| Create User-Activity Diagrams |  | 1 |  |  |  |  | 11 | 1
| Standardize scripting nomenclature | [6 empty] | 10 | 0
| Define class domains | [6 empty] | 7 | 0
| Design database system | [6 empty] | 0 | 0
| Planning and Meeting | 1.2 | 0.67 | 1 | 1.5 | 0.75 |  |  | 4.37
| Define Use Cases | 1.25 | 1 | 0.9 | 0.5 |  |  | 9.42 | 3.65
| Create User-Activity Diagrams |  | 0.85 | 0.5 |  |  |  | 10 | 1.35
| Standardize scripting nomenclature | [6 empty] | 10 | 0
| Define class domains | [6 empty] | 7 | 0
| Logical design | [6 empty] | 5 | 0
| Create entity-relationship diagram | [6 empty] | 6 | 0
| Assess data quality | [6 empty] | 5 | 0
Week 2 | Establish domain attributes |  |  | 1 |  |  |  | 5 | 1
| Normalize | [6 empty] | 2 | 0
| Physical design | [6 empty] | 5 | 0
| Determine hardware and performance requirements | [6 empty] | 4 | 0
| Create Denormalization plan | [6 empty] | 0 | 0
| Create a data dictionary |  |  | 2 |  |  |  | 6 | 2
| total for week | 2.45 | 2.52 | 5.4 | 2 | 0.75
| Design graphical user interface for website | [6 empty] | 6 | 0
| Planning and Meeting | 2 | 1 | 1 | 3.25 | 2 |  |  | 7.25 |  | 10
| Define Use Cases |  |  |  | 0.5 |  |  | 5.77 | 0.5
| Create User-Activity Diagrams |  | 0.25 | 3 |  |  |  | 8.65 | 3.25
| Standardize scripting nomenclature |  |  |  | 0.5 |  |  | 10 | 0.5
| Define class domains | [6 empty] | 7 | 0
| Logical design | [6 empty] | 5 | 0
| Create entity-relationship diagram |  | 1.2 |  |  |  |  | 6 | 1.2
| Assess data quality |  |  | 2 |  |  | 100 | 5 | 2
| Establish domain attributes | [6 empty] | 4 | 0
| Normalize |  |  |  | 1 |  | 60 | 2 | 1
| Physical design | [6 empty] | 5 | 0
| Determine hardware and performance requirements |  |  | 0.5 |  |  | 60 | 4 | 0.5
| Determine design requirements | 1 | [5 empty] | 5 | 1
Week 3 | Sketch the wireframe | 3 | [5 empty] | 10 | 3
| Define the style theme | [5 empty] | 25 | 10 | 0 | no time has been spent on this task, how did it get to 25%?
| Design quality assurance (QA) tests | [6 empty] | 10 | 0
| total for week | 6 | 2.45 | 6.5 | 5.25 | 2
| Planning & Meeting | 4.5 | 3.5 | 1.85 | 5.25 | 8.3 |  |  | 15.1
| Create user-acceptance tests |  | 1.5 |  |  |  | 15 | 14 | 1.5
| Define class domains |  |  |  | 0.75 |  | 90% | 7 | 0.75
Week 4 | Standardize scripting nomenclature(SSDs) |  |  |  | 3.5 |  | 75% | 9.5 | 3.5
| Create User-Activity Diagrams |  |  |  | 0.25 |  | 100% | 5.4 | 0.25
| Create entity-relationship diagram | [5 empty] | 20 | 4.8 | 0
| Establish domain attributes |  |  | 1.5 |  |  | 85 | 4 | 1.5
| Create Denormalization plan |  |  |  | 0.25 |  | 100 | 0 | 0.25 | To best access user information without Joins (improves query performance), all personal user information will be kept under the same UserProfile table. User account information will be kept separate.
| Create a data dictionary |  |  | 0.5 |  |  | 95 | 4 | 0.5
| Create system-integration test |  | 1.2 |  |  |  | 15 | 10 | 1.2
| Define Use Cases | 2 |  |  |  | 0.5 | 95 | 5.27 | 2
| Determine design requirements | [5 empty] | 20 | 4 | 0 | For design requirement; reduce time required for style theme, whereas wireframe takes more time
| Sketch the wireframe | 2.5 |  |  |  |  | 90 | 10 | 2.5
| Create module test |  | 2 |  |  |  | 20% | 10 | 2
Future Tasks
| Normalize data |  |  | 1 |  |  | 15% | 18 | 1
| total for week | 9 | 8.2 | 3.85 | 10 | 8.8 |  |  | 31.05
| Development | [7 empty] | 0
Week 5 | Planning & Meeting | 3.5 | 2 | 2 | 3 | 4 |  |  | 10.5
Carryover Tasks
| Create entity-relationship diagram |  |  |  | 3 |  | 90% | 4.8 | 3
| Sketch the wireframe | [5 empty] | 90 | 7.5 | 0
| Design quality assurance (QA) tests |  |  | 2 |  | 1 | 20 | 10 | 2
Scheduled Tasks
| Create Database System: | [6 empty] | 36 | 5.5
| Create Class Domains |  |  |  | 1 |  | 90% |  | 1
| Style Theme | 3 |  |  | 0.5 |  | 20% |  | 3.5
Future Tasks
| Create User Interface | 0.5 |  |  | 0.5 |  | 0.5% | 26 | 1
| Total for Week 5 | 6.5 | 2 | 4 | 7.5 | 5 |  |  | 20
Week 6 | Planning and Meeting | 2.85 | 2 | 2.55 | 4.5 | 0.3 |  | 3 | 11.9
Carryover Tasks
| Design quality assurance (QA) tests |  |  | 2.5 |  |  | 65% | 8 | 2.5
| Sketch the wireframe | 5 |  |  |  |  | 98% | 7.5 | 5
| Style Theme | 0.75 |  |  |  |  | 25% |  | 0.75
| ER Diagram |  |  |  | 0.25 |  | 95% |  | 0.25
| Class Domains |  |  |  | 0.25 |  | 95% |  | 0.25
| Standardize Nomenclature |  |  |  | 1.5 |  | 95% |  | 1.5
| Use Cases |  |  |  | 1.5 |  | 95% |  | 1.5
Scheduled Tasks
| Create user interface (UI) | 0.75 |  |  |  |  | 0.5% | 25 | 0.75
| Create help guide UI features | [6 empty] | 18 | 0
| Future Tasks |  | 0.95 |  |  |  | 25%
Create UI-DB scripts
| Java script templates for authentication |  | 9.5 |  |  |  | 90%
| Total for Week 6 | 9.35 | 12.45 | 5.05 | 8 | 0.3 |  |  | 34.85
Week 7 | Planning & Meeting | 2.5 | 2 | 0.75 | 4 | 3 |  | 3 | 9.25
| Carryover Tasks | [7 empty] | 0
| Design quality assurance (QA) tests |  |  | 3 |  |  | 95% | 5.5 | 3
| Create user interface (UI) | 4 |  |  | 0.5 |  | 5% | 24.25 | 4.5
| Sketch the wireframe | 2 |  |  |  |  | 100% | 2.5 | 2
| Obtain Website |  |  | 1.5 |  |  | 100% |  | 1.5
| ER Diagram |  |  |  | 0.8 |  | 100% |  | 0.8
| Class Domains |  |  |  | 0.8 |  | 100% |  | 0.8
| Use Cases |  |  |  | 1.4 |  | 100% |  | 1.4
| Scheduled Tasks | [7 empty] | 0
| Create UI-DB scripts | [6 empty] | 25 | 0
| Create Tool Tips | [6 empty] | 38 | 0
| (PHP) how to send email from an email server |  | 6 | [5 empty] | 6
| Java script templates for authentication |  | 2
| Future Tasks | [7 empty] | 0
| normalize data |  |  | 0.5 |  |  |  |  | 0.5
| Total for Week 7 | 8.5 | 10 | 5.75 | 7.5 | 3 |  |  | 31.75
Week 8 | Planning & Meeting | 1.3 | 6 | 1.33 | 2.25 | 1.3 |  |  | 10.88
| Scheduled Tasks | [7 empty] | 0
| Create script to import data to table |  |  | 2.3 |  |  | 40% |  | 2.3
| Create database tables |  |  |  | 6 |  | 90% |  | 6 |  | 90
| Create user interface (UI) | 10 |  |  |  |  | 55% |  | 10
| editing sample data for import |  |  | 2.5 | 4.25 |  | 100% |  | 6.75
0
| Create technical documentation | [6 empty] | 38 | 0
| Total for Week 8 | 11.3 | 6 | 6.13 | 12.5 | 1.3 |  |  | 35.93
Week 9 | Planning & Meeting | 2 | 2 | 2.75 | 1.75 | 12 |  | 3 | 8.5
| Create database tables |  |  |  | 0.25 |  | 91% |  | 0.25
| Create script to import data to table |  |  | 0.5 | 1.25 |  | 100% |  | 1.75
| Code Login page (create UI-db) |  |  |  | 1 |  | 5% |  | 1
| Code directory (create UI-db) |  |  |  | 2.75 |  | 10% |  | 2.75
| Create user interface (UI) | 9 |  |  |  |  | 75% |  | 9
| Use Cases |  |  | 0.6 |  |  |  |  | 0.6
| Perform module test | [7 empty] | 0
| Save/submit script for update user |  | 8 |  |  |  | 50% |  | 8
| Design quality assurance (QA) tests |  |  | 3 |  |  | 98% | 2.5 | 3
| DB module test | [7 empty] | 0
| UI module test | [7 empty] | 0
| Total for Week 9 | 11 | 10 | 6.85 | 7 | 12 |  |  | 34.85
Week 10 | Planning & Meeting | 2.5 | 2 | 2 | 1.5 | 8 |  |  | 8
| Scheduled Tasks | [7 empty] | 0
| Create user interface (UI) | 5 | [6 empty] | 5
| Create UI-DB scripts | [7 empty] | 0
| Update Directory |  |  |  | 6 |  |  |  | 6
| Show Profile | [7 empty] | 0
| Edit Profile | [7 empty] | 0
| Change Password | [7 empty] | 0
| Logout |  | 1 | [5 empty] | 1
| Search | [7 empty] | 0
| Create User |  |  | 0.75 |  |  |  |  | 0.75
| Create Line | [7 empty] | 0
| Total for Week 10 | 7.5 | 3 | 2.75 | 7.5 | 8 |  |  | 20.75
Week 11 | Planning & Meeting | 2.5 | 0.5 | 1.2 | 2
Scheduled Tasks
| Create user interface (UI) | 3 |  |  |  |  | 85%
| Design quality assurance (QA) tests | 2 |  |  |  | 1
Create UI-DB scripts
| RegularDirectory |  |  |  | 3.5 |  | 100%
| Show Profile |  |  |  | 3.25 |  | 95%
Edit Profile
| Confirm script for delete |  | 3 |  |  |  | 60%
| Login script |  | 4 |  |  |  | 75%
| Save and submit script |  | 5 |  |  |  | 100%
| Add user |  |  | 3
| QA testing |  |  | 1
| Normalize data | [5 empty] | 30%
| Total for Week 11 | 7.5 | 12.5 | 5.2 | 8.75 | 1 |  |  | 33.95
Week 12 | Planning & Meeting | 2.5 | 6 | 1 |  |  |  |  | 9.5
| Scheduled Tasks | [7 empty] | 0
| Testing | [7 empty] | 0
| Create user interface (UI) | 5.5 |  |  |  |  | 90%
| ACL |  |  |  | 5.5 |  | 50%
| User Profile (display; not edit) |  |  |  | 1.5 |  | 100%
| script for add user |  |  | 4 |  |  | 60%
| Total for Week 12 | 8 | 6 | 5 | 7 | 0 |  |  | 26
Week 13 | Planning & Meeting | 1 | 1 | 1.8 | 1 | 2 |  |  | 4.8
Carryover Tasks
| Create user interface (UI) - includes researching on compatibility | 5.5 |  |  |  |  | 95% | 0 | 5.5
| ACL |  |  |  | 6.5 |  | 85% | 0 | 6.5
| script for add user |  |  | 1.5 |  |  |  | 0 | 1.5
| Scheduled Tasks |  | 3
[8 empty] | 36 | 31.4
| Total for Week 13 | 6.5 | 4 | 3.3 | 7.5 | 2 |  |  | 23.3
Week 14 | Planning & Meeting | 3 | 0.6 | 1.5 | 2 | 5.6 |  |  | 7.1
| Scheduled Tasks | [7 empty] | 0
| Testing |  |  | 1 |  |  |  |  | 1
| Create user interface (UI) | 2 |  |  |  |  | 100%
| Create UI-DB scripts | 2.5 |  | 7 | 7.5
| ACL |  |  |  | 3.75 |  | 100%
Add user
| profileEdit |  |  |  | 12
| Login |  |  |  | 2.25 |  | 100%
| Regular Directory | [5 empty] | 100%
Add line
| QA |  | 3 | 1.5
| AdminDir | [5 empty] | 100%
| Total for Week 14 | 7.5 | 3.6 | 11 | 27.5 | 5.6 |  |  | 55.2
Week 15 | Planning & Meeting | 3.25 |  | 1.4 | 2 | 6 |  |  | 6.65
| Scheduled Tasks | [7 empty] | 0
| Testing | 2.5 |  | 4 |  |  |  |  | 6.5
| Create user interface (UI) | [5 empty] | 100%
| Create UI-DB scripts | 1.25 |  |  | 4.5 |  | 100%
ACL
| Add user |  |  | 1
Login
Regular Directory
| Add line |  |  | 1
| QA |  | 2 |  | 5.3
AdminDir
| Total for Week 15 | 7 | 2 | 7.4 | 11.8 | 6 |  |  | 34.2
Week 16 | Planning & Meeting | 4 |  | 1.97 | 2.5 | 3.75
| QA |  |  |  | 1
| Reporting | 2 |  |  |  | 3
| Total for Week 16 | 6 | 0 | 1.97 | 3.5 | 6.75 |  |  | 18.22

## Sheet2
16
|  | Sue | Peres | Ingrid | Luis | PM | % complete | Planned Hours | hours spent
| Diagram user-system interaction |  |  |  |  | 2 |  | 2 | 0
| Planning and Meeting | 1.42 | 1.2 | 1.1 | 1.2 |  |  |  | 4.92
Week 1 | Define Use Cases |  |  | 0.33 | 0.25 |  |  | 10 | 0.58 |  | 11.7 | 6.87 | 7.17
| Create User-Activity Diagrams |  | 1 |  |  |  |  | 11 | 1
| Standardize scripting nomenclature | [6 empty] | 10 | 0
| Define class domains | [6 empty] | 7 | 0
| Design database system | [6 empty] | 0 | 0
| Planning and Meeting | 1.2 | 0.67 | 1 | 1.5 | 0.75 |  |  | 4.37
| Define Use Cases | 1.25 | 1 | 0.9 | 0.5 |  |  | 9.42 | 3.65
| Create User-Activity Diagrams |  | 0.85 | 0.5 |  |  |  | 10 | 1.35
| Standardize scripting nomenclature | [6 empty] | 10 | 0
| Define class domains | [6 empty] | 7 | 0
| Logical design | [6 empty] | 5 | 0
| Create entity-relationship diagram | [6 empty] | 6 | 0
| Assess data quality | [6 empty] | 5 | 0
Week 2 | Establish domain attributes |  |  | 1 |  |  |  | 5 | 1
| Normalize | [6 empty] | 2 | 0
| Physical design | [6 empty] | 5 | 0
| Determine hardware and performance requirements | [6 empty] | 4 | 0
| Create Denormalization plan | [6 empty] | 0 | 0
| Create a data dictionary |  |  | 2 |  |  |  | 6 | 2
| total for week | 2.45 | 2.52 | 5.4 | 2 | 0.75
| Design graphical user interface for website | [6 empty] | 6 | 0
| Planning and Meeting | 2 | 1 | 1 | 3.25 | 2 |  |  | 7.25 |  | 10
| Define Use Cases |  |  |  | 0.5 |  |  | 5.77 | 0.5
| Create User-Activity Diagrams |  | 0.25 | 3 |  |  |  | 8.65 | 3.25
| Standardize scripting nomenclature |  |  |  | 0.5 |  |  | 10 | 0.5
| Define class domains | [6 empty] | 7 | 0
| Logical design | [6 empty] | 5 | 0
| Create entity-relationship diagram |  | 1.2 |  |  |  |  | 6 | 1.2
| Assess data quality |  |  | 2 |  |  | 100 | 5 | 2
| Establish domain attributes | [6 empty] | 4 | 0
| Normalize |  |  |  | 1 |  | 60 | 2 | 1
| Physical design | [6 empty] | 5 | 0
| Determine hardware and performance requirements |  |  | 0.5 |  |  | 60 | 4 | 0.5
| Determine design requirements | 1 | [5 empty] | 5 | 1
Week 3 | Sketch the wireframe | 3 | [5 empty] | 10 | 3
| Define the style theme | [5 empty] | 25 | 10 | 0 | no time has been spent on this task, how did it get to 25%?
| Design quality assurance (QA) tests | [6 empty] | 10 | 0
| total for week | 6 | 2.45 | 6.5 | 5.25 | 2
| Planning & Meeting | 4.5 | 3.5 | 1.85 | 5.25 | 8.3 |  |  | 15.1
| Create user-acceptance tests |  | 1.5 |  |  |  | 15 | 14 | 1.5
| Define class domains |  |  |  | 0.75 |  | 90% | 7 | 0.75
Week 4 | Standardize scripting nomenclature(SSDs) |  |  |  | 3.5 |  | 75% | 9.5 | 3.5
| Create User-Activity Diagrams |  |  |  | 0.25 |  | 100% | 5.4 | 0.25
| Create entity-relationship diagram | [5 empty] | 20 | 4.8 | 0
| Establish domain attributes |  |  | 1.5 |  |  | 85 | 4 | 1.5
| Create Denormalization plan |  |  |  | 0.25 |  | 100 | 0 | 0.25 | To best access user information without Joins (improves query performance), all personal user information will be kept under the same UserProfile table. User account information will be kept separate.
| Create a data dictionary |  |  | 0.5 |  |  | 95 | 4 | 0.5
| Create system-integration test |  | 1.2 |  |  |  | 15 | 10 | 1.2
| Define Use Cases | 2 |  |  |  | 0.5 | 95 | 5.27 | 2
| Determine design requirements | [5 empty] | 20 | 4 | 0 | For design requirement; reduce time required for style theme, whereas wireframe takes more time
| Sketch the wireframe | 2.5 |  |  |  |  | 90 | 10 | 2.5
| Create module test |  | 2 |  |  |  | 20% | 10 | 2
Future Tasks
| Normalize data |  |  | 1 |  |  | 15% | 18 | 1
| total for week | 9 | 8.2 | 3.85 | 10 | 8.8 |  |  | 31.05
| Development | [7 empty] | 0
Week 5 | Planning & Meeting | 3.5 | 2 | 2 | 3 | 4 |  |  | 10.5
Carryover Tasks
| Create entity-relationship diagram |  |  |  | 3 |  | 90% | 4.8 | 3
| Sketch the wireframe | [5 empty] | 90 | 7.5 | 0
| Design quality assurance (QA) tests |  |  | 2 |  | 1 | 20 | 10 | 2
Scheduled Tasks
| Create Database System: | [6 empty] | 36 | 5.5
| Create Class Domains |  |  |  | 1 |  | 90% |  | 1
| Style Theme | 3 |  |  | 0.5 |  | 20% |  | 3.5
Future Tasks
| Create User Interface | 0.5 |  |  | 0.5 |  | 0.5% | 26 | 1
| Total for Week 5 | 6.5 | 2 | 4 | 7.5 | 5 |  |  | 20
Week 6 | Planning and Meeting | 2.85 | 2 | 2.55 | 4.5 | 0.3 |  | 3 | 11.9
Carryover Tasks
| Design quality assurance (QA) tests |  |  | 2.5 |  |  | 65% | 8 | 2.5
| Sketch the wireframe | 5 |  |  |  |  | 98% | 7.5 | 5
| Style Theme | 0.75 |  |  |  |  | 25% |  | 0.75
| ER Diagram |  |  |  | 0.25 |  | 95% |  | 0.25
| Class Domains |  |  |  | 0.25 |  | 95% |  | 0.25
| Standardize Nomenclature |  |  |  | 1.5 |  | 95% |  | 1.5
| Use Cases |  |  |  | 1.5 |  | 95% |  | 1.5
Scheduled Tasks
| Create user interface (UI) | 0.75 |  |  |  |  | 0.5% | 25 | 0.75
| Create help guide UI features | [6 empty] | 18 | 0
| Future Tasks |  | 0.95 |  |  |  | 25%
Create UI-DB scripts
| Java script templates for authentication |  | 9.5 |  |  |  | 90%
| Total for Week 6 | 9.35 | 12.45 | 5.05 | 8 | 0.3 |  |  | 34.85
Week 7 | Planning & Meeting | 2.5 | 2 | 0.75 | 4 | 3 |  | 3 | 9.25
| Carryover Tasks | [7 empty] | 0
| Design quality assurance (QA) tests |  |  | 3 |  |  | 95% | 5.5 | 3
| Create user interface (UI) | 4 |  |  | 0.5 |  | 5% | 24.25 | 4.5
| Sketch the wireframe | 2 |  |  |  |  | 100% | 2.5 | 2
| Obtain Website |  |  | 1.5 |  |  | 100% |  | 1.5
| ER Diagram |  |  |  | 0.8 |  | 100% |  | 0.8
| Class Domains |  |  |  | 0.8 |  | 100% |  | 0.8
| Use Cases |  |  |  | 1.4 |  | 100% |  | 1.4
| Scheduled Tasks | [7 empty] | 0
| Create UI-DB scripts | [6 empty] | 25 | 0
| Create Tool Tips | [6 empty] | 38 | 0
| (PHP) how to send email from an email server |  | 6 | [5 empty] | 6
| Java script templates for authentication |  | 2
| Future Tasks | [7 empty] | 0
| normalize data |  |  | 0.5 |  |  |  |  | 0.5
| Total for Week 7 | 8.5 | 10 | 5.75 | 7.5 | 3 |  |  | 31.75
Week 8 | Planning & Meeting | 1.3 | 6 | 1.33 | 2.25 | 1.3 |  |  | 10.88
| Scheduled Tasks | [7 empty] | 0
| Create script to import data to table |  |  | 2.3 |  |  | 40% |  | 2.3
| Create database tables |  |  |  | 6 |  | 90% |  | 6 |  | 90
| Create user interface (UI) | 10 |  |  |  |  | 55% |  | 10
| editing sample data for import |  |  | 2.5 | 4.25 |  | 100% |  | 6.75
0
| Create technical documentation | [6 empty] | 38 | 0
| Total for Week 8 | 11.3 | 6 | 6.13 | 12.5 | 1.3 |  |  | 35.93
Week 9 | Planning & Meeting | 2 | 2 | 2.75 | 1.75 | 12 |  | 3 | 8.5
| Create database tables |  |  |  | 0.25 |  | 91% |  | 0.25
| Create script to import data to table |  |  | 0.5 | 1.25 |  | 100% |  | 1.75
| Code Login page (create UI-db) |  |  |  | 1 |  | 5% |  | 1
| Code directory (create UI-db) |  |  |  | 2.75 |  | 10% |  | 2.75
| Create user interface (UI) | 9 |  |  |  |  | 75% |  | 9
| Use Cases |  |  | 0.6 |  |  |  |  | 0.6
| Perform module test | [7 empty] | 0
| Save/submit script for update user |  | 8 |  |  |  | 50% |  | 8
| Design quality assurance (QA) tests |  |  | 3 |  |  | 98% | 2.5 | 3
| DB module test | [7 empty] | 0
| UI module test | [7 empty] | 0
| Total for Week 9 | 11 | 10 | 6.85 | 7 | 12 |  | 5.5 | 34.85
Week 10 | Planning & Meeting | 2 |  | 2 | 1.5 | 3 |  |  | 5.5
| Scheduled Tasks | [7 empty] | 0
| Create user interface (UI) | 3.5 | [6 empty] | 3.5
| Create UI-DB scripts | [7 empty] | 0
| Update Directory |  |  |  | 6 |  |  |  | 6
| Show Profile | [7 empty] | 0
| Edit Profile | [7 empty] | 0
| Change Password | [7 empty] | 0
| Logout | [7 empty] | 0
| Search | [7 empty] | 0
| Create User |  |  | 0.75 |  |  |  |  | 0.75
| Create Line | [7 empty] | 0
0
0
Week 11
| Normalize data | [5 empty] | 30%